## Goal 1
CAFE Department of Plant and Soil Sciences Work-Life Goals 2015-2016
Goal 1
Improve empowerment statement 6 response 'I am satisfied with the procedures available for resolving faculty/staff complaints'
| Friday, April 8, 2016 | Friday, July 1, 2016 | Monday, October 3, 2016 | Friday, January 13, 2017 | Monday, April 3, 2017 | Friday, July 7, 2017
Objective, Initiative, Action Step Addressed in Strategic Plan: Goal 3 Recruit, develop and retain exceptional faculty and staff | Recruit, develop and retain exceptional faculty and staff | Recruit, develop and retain exceptional faculty and staff | Recruit, develop and retain exceptional faculty and staff | Recruit, develop and retain exceptional faculty and staff
Metrics Chosen: Qualitative progress towards defining available processes and informing employees | Qualitative progress towards defining available processes and informing employees | Qualitative progress towards defining available processes and informing employees | Qualitative progress towards defining available processes and informing employees | Qualitative progress towards defining available processes and informing employees
Assessment Method/Tools: We will provide quarterly progress reports | We will provide quarterly progress reports | We will provide quarterly progress reports | We will provide quarterly progress reports | We will provide quarterly progress reports
Target: Define the steps necessary and demonstrate incremental progress towards reaching this goal | Define the steps necessary and demonstrate incremental progress towards reaching this goal | Define the steps necessary and demonstrate incremental progress towards reaching this goal | Define the steps necessary and demonstrate incremental progress towards reaching this goal | Define the steps necessary and demonstrate incremental progress towards reaching this goal
Improvement Actions: Step 1 is to appoint a staff/faculty working group to define the subsequent steps | Step 1 is to appoint a staff/faculty working group to define the subsequent steps | The committee developed and circulated a survey to determine the background for the low favorable responses to the statement 'I am satisfied with the procedures available for resolving faculty and staff complaints.’ | The committee has developed the first draft of a document on where to register and how to address different types of complaints.
Resources Applied: Chair, faculty and staff time will be required | Chair, faculty and staff time will be required | A committee of four staff and faculty members is working on this goal.
Results | A committee of four faculty and staff members met to discuss the process. They developed a four question survey to receive input on the major complaint types which should be addressed. | 40 department members replied to the survey. 14 of 40 acknowledged having complaints. Complaints range widely from facilities to coworkers, supervisors, job responsibilities, and pay. 15 of 40 respondents did not know how to register a complaint if they had one. Some respondents feared retaliation. | The document is under review. It will be circulated in the department for comments about its value and whether it encompasses the full spectrum of complaints. | The committee has developed the document on where to register and how to address different types of complaints. The document will be posted on the department web site. | The progress remains unchanged since January. Posting the created document will be the final step under this goal. | The document 'PSS expressing a concern' was posted on the department web site, June 2017.
Interpretation of Results | The department group has begun working on this goal, creating the committee which developed the survey is incremental progress | It is important for department members to know, or be able to find out, how and to whom to report a complaint. 40 responses is about 1/3 of the department's staff and faculty. Similarly, 39 department members responded to the original UK@Work survey. Perhaps 2/3 of the department does not view this as a critical problem or does not want to spend time on this activity. Perhaps they didn't want to respond because they worried about retaliation.
Reflection on Improvement Actions | We must understand the department's response to the UK@Work survey question before we identify/modify the procedures | The committee will develop a document on where to register and how to address different types of complaints. The document will be circulated department-wide. The committee will seek input from the department chair. |  | It has been difficult to anticipate the myriad types of potential complaints. The committee settled on 1) facility complaints, 2) employment problems, questions and concerns, 3) and harassment or discrimination issues as the most frequent or most serious types of issues to consider. | The situation remains unchanged since January. | This is the final planned step for this goal.

## Goal 2
CAFE Department of Plant and Soil Sciences Work-Life Goals 2015-2016
Goal 2
Improve Work relationship statement 6 response 'Differing opinions are openly discussed in reaching decisions in my department'
| Friday, April 8, 2016 | Friday, July 1, 2016 | Monday, October 3, 2016 | Friday, January 13, 2017 | Monday, April 3, 2017 | Friday, July 7, 2017
Objective, Initiative, Action Step Addressed in Strategic Plan: Goal 3 Recruit, develop and retain exceptional faculty and staff | Recruit, develop and retain exceptional faculty and staff | Recruit, develop and retain exceptional faculty and staff | Recruit, develop and retain exceptional faculty and staff | Recruit, develop and retain exceptional faculty and staff | Recruit, develop and retain exceptional faculty and staff | Recruit, develop and retain exceptional faculty and staff
Metrics Chosen: Qualitative progress towards improving communications which will include acknowledging and discussing multiple opinions | Qualitative progress towards improving communications which will include acknowledging and discussing multiple opinions | Qualitative progress towards improving communications which will include acknowledging and discussing multiple opinions | Qualitative progress towards improving communications which will include acknowledging and discussing multiple opinions | Qualitative progress towards improving communications which will include acknowledging and discussing multiple opinions | Qualitative progress towards improving communications which will include acknowledging and discussing multiple opinions | Qualitative progress towards improving communications which will include acknowledging and discussing multiple opinions
Assessment Method/Tools: We will provide quarterly progress reports | We will provide quarterly progress reports | We will provide quarterly progress reports | We will provide quarterly progress reports | We will provide quarterly progress reports | We will provide quarterly progress reports | We will provide quarterly progress reports
Target: Identify and implement steps needed for improved departmental communication | Identify and implement steps needed for improved departmental communication | Identify and implement steps needed for improved departmental communication | Identify and implement steps needed for improved departmental communication | Identify and implement steps needed for improved departmental communication | Identify and implement steps needed for improved departmental communication | Identify and implement steps needed for improved departmental communication
Improvement Actions: Step 1 is to appoint a staff/faculty working group to define the subsequent steps | Step 1 is to appoint a staff/faculty working group to define the subsequent steps | The committee is developing an internal department survey to assess why department responses were ~50% positive to the statement ‘Differing opinions are openly discussed in reaching decisions in my department’ | A survey invitation was distributed to all known faculty and staff email addresses (161) in PSS department in August 2016.  60 survey respondents representing 37.3% of overall department faculty and staff employees.  Affiliation: 61% staff, 39% faculty  Work location: 38% PSB, 32% AGN, 10% Spindletop, 10% off campus, 10% other (inc. KTRDC)
Resources Applied: Chair, faculty and staff time will be required | Chair, faculty and staff time will be required | A committee of five faculty and staff members is working on this goal.
Results | A committee of five faculty and staff members met to discuss the process. They subsequently described their proposed process at the department's March staff meeting. | The survey has not been circulated, so we have no additional results. | Best way to be informed - 95% email/listserv, 5% specific meetings Best way to express opinion: 42% Meetings, 34% online “suggestion box” Communication roadblocks: 51% decisions made outside department without department knowledge, 39% decisions made without consulting department, 32% decisions made within department without faculty/staff knowledge | Based on survey results, an electronic and anonymous suggestion box will be developed this quarter and made 'live' to the department. Specifics will be discussed with IT person, Jacob, to implement as soon as feasible. We will announce to department about it via all departmental listservs. | The electronic and anonymous suggestion box was developed and announced at the March department staff meeting. As of now several technical difficulties with insuring anonymity have not been resolved, so the electronic suggestion box is not yet live. | The electronic and anonymous suggestion box was made available and announced to the department May 17. A link is present on the department internal home page.
Interpretation of Results | The department group has begun working on this goal; creating the committee which has met once is incremental progress |  | Size and dispersal of department may influence communication. Need to discuss ways to disseminate information from both within and outside department meetings that may affect the employees or facilities of this department. Need to address new avenues for employees to express opinions or thoughts regarding interdepartmental issues. |  |  | No comments have been submitted to the suggestion box. So at this time there is not a backlog of opinions which the department has felt have gone unheard.
Reflection on Improvement Actions | We must understand the department's response to the UK@Work survey question before we identify ways to obtain more opinions. | The survey needs to be circulated soon. | Committee will meet again in early December to discuss the recommendations of specific changes that address the outcomes that were discussed in this report, based on survey response. | For our April meeting/deadline, we hope to analyze the usage of the newly implemented e-suggestion box and to make further recommendation to either disable or continue based on the effectiveness and usage of the e-suggestion box. | For our July meeting/deadline, we hope to analyze the usage of the newly implemented e-suggestion box and to make further recommendation to either disable or continue based on the effectiveness and usage of the e-suggestion box. | The suggestion box will remain active. This will be another option for department members to make their opinions heard.